## ProductBackLog
Project Name:SUBTRACK Group Members:Aral Cavlak, Samet Berat Şeker, Aykan Uğur, Özge Bostan, Ceyda Ece Han, Mehmet Mert Eser, Mustafa Çağlar Cömert
# | Product BackLog
1 | Database Planning
2 | App is going to have security features (such as 2-Step-Verification, Firewall etc.)
3 | Display a list of available subscription with basic information.
4 | Automatically divides payments among users for shared subscription systems.
5 | Show detailed information for each subscription (e.g., description, upcoming pricing).
6 | Allowing the user to subscribe, unsubscribe, and manage their subscriptions.
7 | Application is going to process payment as a BaaS.
8 | Import and scan subscriptions from payments, and manage subscription statuses.
9 | Allowing users to see recent campaigns and deals they can benefit from.
10 | Allow users to rate and review subscription, contributing to a community-driven experience.
11 | Ensure the app is optimized for various devices with an engaging user interface.
12 | Users to be able to add to their balance, use it as a bank alternative for annual or monthly payments.
13 | Allowing the user to save their cards to their account.
14 | App to be able to send notifications about payments, balances, cost updates, news and etc.
15 | Shows users graphs of their usage and savings with subscriptions.
16 | The user will be able to find which subscription contains the desired content based on the country or region.
17 | The user can earn cash by inviting other users with an invitation code.
18 | Application desing will have a customizable and user-friendly interface.
19 | There will be accessibility options for users with disabilities.
20 | Preparing User Guideline and Tutorials.

## Sprint-1
SPRINT-1
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer, Product Owner | Database Planning | Ready to Start | High | 2025-06-10 | 2025-06-13 | 3 | Our database should be unique, secure, and as compliant with 4NF rules as possible.
Developer,Designer | Application desing will have a customizable and user-friendly interface. | Ready to Start | Medium | 2025-06-13 | 2025-06-15 | 2 | A well-categorized, fast interface with color selection that does not strain the user's eyes.
Developer,Designer | Display a list of available subscription with basic information. | Ready to Start | High | 2025-06-15 | 2025-06-16 | 1 | A system that operates based on the preview logic of subscriptions.
Developer | Allowing the user to subscribe, unsubscribe, and manage their subscriptions without payment. | Ready to Start | Medium | 2025-06-16 | 2025-06-18 | 2 | This core system needs to be built before the payment section is implemented.
33
BACKLOG
Formulas:
FINISH = [START]+[DURATION (DAYS)]
START = [FINISH, row above]
As a developer, I want to create a system that presents a preview of available subscriptions as a list to provide a clear overview.
STATUS: Ready to Start
POINTS: 5
As a user, I want to see a customizable interface with a variety of color selections that is easy to use.
STATUS: Ready to Start
POINTS: 10
Dev
Dev
As a developer, I want to design and plan a database that follows 4NF principles, ensuring minimal redundancy and high security.
STATUS: Ready to Start
POINTS: 8
PO
Dev
As a developer, I want to implement a user account system to securely store user data, including card information and subscription details.
STATUS: Ready to Start
POINTS: 5
Designer
As a developer, I want to build a backend system that enables users to subscribe, unsubscribe, and manage their subscriptions without payment, ensuring smooth functionality.
STATUS: Ready to Start
POINTS: 5
Dev
Dev

## Sprint-2
SPRINT-2
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer,Designer | Show detailed information for each subscription (e.g., description, upcoming pricing). | Not Started | Medium | 2025-06-18 | 2025-06-20 | 2 | Make the app easy to use with clear subscription details and price updates.
Developer,Designer | Import and scan subscriptions from payments, and manage subscription statuses. | Not Started | Low | 2025-06-20 | 2025-06-23 | 3 | Let users track, manage, and cancel subscriptions easily.
Developer | Allowing users to see recent campaigns and deals they can benefit from. | Not Started | Low | 2025-06-23 | 2025-06-27 | 4 | We are trying to make our app more attractive to the new users, so, we are going to launch campaigns with the companies who offer subscription services. That way the users can reduce their payments.
Developer,Designer | Allowing the user to save their cards to their account. | Not Started | High | 2025-06-27 | 2025-06-28 | 1 | Store cards safely and let users add or remove them easily.
10
BACKLOG
Formulas:
FINISH = [START]+[DURATION (DAYS)]
START = [FINISH, row above]
As a user, I wouldn't use any applications that don't seem safe to me. Especially the ones that require payments. I want to see the security features as much
as possible.
STATUS: Not Started
As a user, I want to see the price history and what i've already paid for a subscription. It may not be worth it if i don't even use it as much.
STATUS: Not Started
Dev
As a user, I don't want to spend any money on the subscriptions than i approve of. Let me know when the corparation wants to get more money out of me.
STATUS: Not Started
Dev
Designer
Dev
As a user, I may not want to use the service if i cannot add my virtual credit card in. That makes me feel more safe and in control.
STATUS: Not Started
Dev

## Sprint-3
SPRINT-3
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer, Product Owner | Application is going to process payment as a BaaS (Banking as a Service). | Not Started | High | 2025-08-28 | 2025-08-31 | 3 | Ensuring secure and seamless payment processing will be crucial for the app's reliability and user trust.
Developer,Designer | Users to be able to add to their balance, use it as a bank alternative for annual or monthly payments. | Not Started | High | 2025-08-31 | 2025-09-02 | 2 | Providing a banking alternative adds flexibility, but strong security measures are crucial for reliability.
Developer | App to be able to send notifications about payments, balances, cost updates, news and etc. | Not Started | Low | 2025-09-02 | 2025-09-04 | 2 | Notifications keep users informed, but they should be well-timed to avoid being disruptive.
Developer, Product Owner | Automatically divides payments among users for shared subscription systems. | Not Started | High | 2025-09-04 | 2025-09-07 | 3 | Lots of people use shared subscription accounts with their families and friends. This way they can easily split their payments.
Developer | Shows users graphs of their usage and savings with subscriptions. | Not Started | Low | 2025-09-07 | 2025-09-08 | 1 | Clear visualizations help users track spending patterns and manage finances more effectively.
11
BACKLOG
Formulas:
FINISH = [START]+[DURATION (DAYS)]
START = [FINISH, row above]
As a user, I want the application to securely process my payments with a reliable system so that I can complete transactions without delays or security concerns.
STATUS: Not Started POINTS: 15
As a user, I want to receive real-time notifications about my transactions, balance updates, and cost changes so that I am always informed about my financial status.
STATUS: Not Started
POINTS: 3
Dev
As a user, I want to add funds to my balance and use it as an alternative to a bank so that I can manage my finances conveniently and securely within the app.
STATUS: Not Started
POINTS: 10
PO
Dev
Dev
As a user, I want the app to be fully optimized for different devices so that I can have a seamless and engaging experience regardless of the screen size I use.
STATUS: Not Started
POINTS: 7
As a user, I want to see clear and interactive graphs of my spending and savings so that I can track my financial habits, analyze trends, and make better budgeting decisions.
STATUS: Not Started
POINTS: 4
Dev
Dev

## Sprint-4
SPRINT-4
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Ensure the app is optimized for various devices with an engaging user interface. | Not Started | High | 2025-09-08 | 2025-09-12 | 4 | A responsive and intuitive design ensures a smooth experience across different devices.
Developer,Designer | Allow users to rate and review subscription, contributing to a community-driven experience. | Not Started | Low | 2025-09-12 | 2025-09-14 | 2 | Provides users the opportunity to evaluate the services.
Developer,Designer | The user will be able to find which subscription contains the desired content based on the country or region. | Not Started | Low | 2025-09-14 | 2025-09-15 | 1 | A search system for finding which subscribing system to choose.
Developer | The user can earn cash by inviting other users with an invitation code. | Not Started | Medium | 2025-09-15 | 2025-09-16 | 1 | A system to gather users while letting them profit.
Developer | There will be accessibility options for users with disabilities. | Not Started | Low | 2025-09-16 | 2025-09-18 | 2 | A narrator that reads the things on the screen and directs the users.
Developer | App is going to have security features (such as 2-Step-Verification, Firewall etc.) | Not Started | High | 2025-09-18 | 2025-09-21 | 3 | Keep payments secure with strong authentication and regular security checks.
Developer | Preparing User Guidelines and Tutorials. | Not Started | Low | 2025-09-21 | 2025-09-23 | 2 | We are going to prepare videos and texts to inform users and guide them along with their app experience.
11
BACKLOG
Formulas:
FINISH = [START]+[DURATION (DAYS)]
START = [FINISH, row above]
As a user, I would love to lose the burden of having to remind my friends who are using my shared account monthly to pay their share.
STATUS: Not Started POINTS: 8
As a user, I want my father with visual disability to be able to use this app without any problems.
STATUS: Not Started
POINTS: 3
Dev
As a user, I want to be able to see if other users are content with and would recommend certain subscription services.
STATUS: Not Started
POINTS: 5
Dev
Dev
Designer
Designer

## KeyDropdowns
KEY DROPDOWNS - DO NOT DELETE
CATEGORY KEY | PRIORITY KEY | STATUS KEY
Research | High | In Progress
Feature | Medium | Ready to Start
Content | Low | Complete
Task |  | On Hold
Update |  | Testing
Not Started

## Templates
TEMPLATES
ASSIGNED TO | KANBAN CARDS
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0